## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0085 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2535 |  |  | Transmital Date:1/23/2024
Document Title: Structural Drawing For GCS Bridges |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-T-2535 |  |  | Transmital Date:1/23/2024
[5 empty] | CRS No:PEDCO-CRS- BK-GCS-PEDCO-120-ST-DW-0085_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-493761 | 1402/11/30 | ابعاد بازبینی و اصلاح گردید
2 |  |  | 1402-2294-493761 | 1402/11/30 | مدرک ژئوتکنیک به قسمت ریفرنس اضافه گردید
3 |  |  | 1402-2294-493761 | 1402/11/30 | با عنایت به بند 6 (ارسال مدرک به صورت AFC) رویژن مارک درج نگردید
4 |  |  | 1402-2294-493761 | 1402/11/30 | هندریل اضافه گردید
5 |  |  | 1402-2294-493761 | 1402/11/30 | با مدل سه بعدی کنترل گردید
6 |  |  | 1402-2294-493761 | 1402/11/30 | ---
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: