## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0020 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2414 |  |  | Transmital Date:10/9/2023
Document Title: P&ID - LP Flare System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2414 |  |  | Transmital Date: 10/9/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در این مقطع نظر خاصی مطرح نبوده و پیشبرد گام بعدی بلامانع می باشد. |  | 1402-2294-323729 | 1402/08/14 | مورد تایید است.
2 | عمومی: 1- کلیه خطوط درین می بایست با شیب 1% لحاظ شود این مهم در خصوص DRAIN HEADER مورد تاکید کارفرما می باشد |  | 1402-2294-335919 | 1402/08/22 | شیب خطوط drain در مدارک PID برابر با 1:100 در نظر گرفته شده است. در خصوص شیب خط Drain Header به استحضار می رساند، شیب خط مذکور مطابق با طراحی سایت موجود بینک در نظر گرفته شده است.
3 | عمومی: 2-هر نوع تغییر در مدرک ارسالی می بایست به صورت نشان مارک نمایش داده شود در صورت تکرار این مورد مدرک عودت داده خواهد شد |  | 1402-2294-335919 | 1402/08/22 | مورد تایید است.
4 | در این مقطع نظر خاصی مطرح نبوده و پیشبرد گام بعدی بلامانع می باشد. |  | 1402-2294-335919 | 1402/08/22 | مورد تایید است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: