## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0024 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2017 |  |  | Transmital Date: 4/10/2023
Document Title: P&ID - Potable Water System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2017 |  |  | Transmital Date: 4/10/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0024_D06 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | انتشار نسخ سخت با درج مهر AFC جهت فاز بعدی بلامانع می باشد. شایان ذکر است مقادیر پارامترهای این مدرک و دیگر مدارک دارای وابستگی می باشد لازم است هر گونه تغییر در هر مقطعی از پروژه در دیگر مدارک به نحوه مقتضی در این مدرک و بر عکس اعمال گردد (مستقل از تقدم تاخر) |  | 1402-2294-99987 | 1402/03/16 | مورد تایید است.
1 | انتشار نسخ سخت با درج مهر AFC جهت فاز بعدی بلامانع می باشد. شایان ذکر است مقادیر پارامترهای این مدرک و دیگر مدارک دارای وابستگی می باشد لازم است هر گونه تغییر در هر مقطعی از پروژه در دیگر مدارک به نحوه مقتضی در این مدرک و بر عکس اعمال گردد (مستقل از تقدم تاخر) می بایست سایز ولو درین مربوط به TK-2209 برابر با 2" در نظر گرفته شود. |  | 1402-2294-339963 | 1402/08/23 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: