## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0020 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2414 |  |  | Transmital Date:10/9/2023
Document Title: P&ID - LP Flare System |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2414 |  |  | Transmital Date: 10/9/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0020_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظر پیشین: کلیه شیرهای 2 اینچ و بزرگتر از آن به صورت فلنجی نمایش داده شود. به عنوان نمونه شیرهای Utility Connection. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | کلیه شیرهای 2 اینچ و بزرگتر از آن به صورت فلنجی نمایش داده شده است. در صورت مشاهده خواهشمند است موقعیت شیر مد نظر کاملا مشخص گردد.
2 | در برخی موارد، سایز نازل ظروف، با مدرک داده برگ فرآیندی و مکانیکی یکسان نیست. به عنوان نمونه نازل ورودی و خروجی V-2201 در مدرک داده برگ فرآیندی به ترتیب 10 و 12 اینچ می باشد در حالیکه در مدرک P&ID، ء 8 و 10 اینچ نمایش داده شده است. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | اصلاح گردید.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: