## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0025 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2414 |  |  | Transmital Date:10/9/2023
Document Title: P&ID - Glycol Sump Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2414 |  |  | Transmital Date: 10/9/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0025_D07 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تمام شیرهای 2 اینچ و بزرگتر به صورت فلنجس نمایش داده شود. به عنوان نمونه شیر اتصال LT-2292 به نازل L2 و شیر L.O خروجی PSV. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | اعمال گردید.
2 | فرمان Remote Start از DCS به MCC برای موتور پمپ 2204 نمایش داد ه نشده است. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | مطابق Recomendation شماره ۱۲۰گزارش HAZOP پروژه حذف شده است.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-08653 | 2023-10-23 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: