## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-LI-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1009 |  |  | Transmital Date:5/28/2022
Document Title: Critical Line List |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR_1009 |  |  | Transmital Date:5/28/2022
[5 empty] | CRS No: NISOC-BK-GCS-PEDCO-120-PI-LI-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار های طراحی ذکر شده مورد قبول نبوده و می بایست کلاس فلنج در خصوص لوله های داخل واحد زیر 24 اینچ ملاک عمل قرار گیرد از این رو و با توجه به اینکه تععین سطح تحلیل بر مبنای فشار و دما خواهد بود لذا تا زمان نهایی سازی اطلاعات فوق اضهار نظر در خصوص این مدرک امکان پذیر نیست |  | 1401/2294/111570 | 1401/03/31 | بر اساس اخرین مدرک لاین لیست که مورد اشاره شده در ان اعمال گردیده تعیین سطح خطوط انجام شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
Date: