## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-RT-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2343 |  |  | Transmital Date:9/4/2023
Document Title: Stress Analysis Calculations Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-2343 |  |  | Transmital Date:9/4/2023
[5 empty] | CRS No: NISOC-CRS-PEDCO-BK-GCS-PEDCO-120-PI-RT-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در پیوست 10 کتابچه پیمان ذکر گردیده است کلیه محاسبات مربوط به انالیز تنش می بایست توسط نرم افزار ceasar مورد انالیز تنش قرار گیرند و فایل های native انالیز تنش به انضمام نسخه نرم افزار بهمراه گزارش مربوطه جهت بررسی و تایید در اختیار کار فرما قرارداده شود . |  | 1402-2294-2957477 | 1402/07/26 | فایل native استرس انالیز پروژه به پیوست تحت عنوان native ازسال می گرددو همچنین نسخه نرم افزار نیز در این ویرایش به عنوان attachment 1 ارسال می گردد
2 | ضروری است لیست نیروهای وارده به خطوط در جدول جداگانه ابتدای مدرک درج گردد |  | 1402-2294-2957477 | 1402/07/26 | در report نمایش داده شده است
3 | جدول نیروهای وارد بر تکیه گاه ها در مدرک گنجانده شود |  | 1402-2294-2957477 | 1402/07/26 | در report نمایش داده شده است
4 | تغییرات مدرک در صفحه revision record و همچنین متن مدرک نشان داده شود |  | 1402-2294-2957477 | 1402/07/26 | اعمال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri J.Mousazadeh | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 10.Sep.2023 |  |  |  |  | Date: 10.Sep.2023