## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2189 |  |  | Transmital Date: 6/10/2023
Document Title: Data Sheets For Orifice Plate/Restriction Orifice |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2189 |  |  | Transmital Date: 6/10/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0013_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | داده های فرایندی با آخرین رویژن مدارکPFD وP&ID ارسالی همخوانی ندارد لذا میبایست بروزرسانی گردد. |  | 1402-2294-157848 | 1402/04/24 | مدرک مطابق آخرین اطلاعات درج شده در آخرین نسخه مدارک فرایندی به روزرسانی گردید.
ORIFICE PLATE
2 | قبل از ارسال مدرک داده برگ، میبایست مدرک سایزینگ ارايه گردد. |  | 1402-2294-157848 | 1402/04/24 | مدارک پیش نیاز به روز رسانی شده است.
3 | سایز های بدست آمده برای اوریفیس ها ی FE-2131A/B/Cو FE-2131A/B/Cارايه نشده است. |  | 1402-2294-157848 | 1402/04/24 | مدرک مطابق آخرین اطلاعات درج شده در آخرین نسخه مدارک به روزرسانی گردید.
4 | جریان ماکزیمم درج شده برای FE-2271 اشتباه میباشد. |  | 1402-2294-157848 | 1402/04/24 | مدرک مطابق آخرین اطلاعات درج شده در آخرین نسخه مدارک به روزرسانی گردید.
RESTRICTION ORIFICE
5 | فاز سیال برای RO-2144 اصلاح گردد. |  | 1402-2294-157848 | 1402/04/24 | مدرک مطابق آخرین اطلاعات درج شده در آخرین نسخه مدارک به روزرسانی گردید.
6 | سایزینگ انجام شده برای RO-2144 اصلاح گردد. |  | 1402-2294-157848 | 1402/04/24 | مدرک مطابق آخرین اطلاعات درج شده در آخرین نسخه مدارک به روزرسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: