## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0024 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2276 |  |  | Transmital Date: 7/30/2023
Document Title: Calculation Note for Utility Area Sleepers |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2276 |  |  | Transmital Date: 7/30/2023
[5 empty] | CRS No:PEDCO-CRS-BK-GCS-PEDCO-120-ST-CN-0024_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-206677 | 1402/05/25 | فایل محاسبات به همراه نقشه ها ارسال می گردد
2 |  |  | 1402-2294-206677 | 1402/05/25 | این مدرک فاقد دیتا شیت میباشد.
3 |  |  | 1402-2294-206677 | 1402/05/25 | مدرک SINGEL LINE DIAGRAM اضافه گردید.
4 |  |  | 1402-2294-206677 | 1402/05/25 | -
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: