## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0058 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2509 |  |  | Transmital Date: 11/25/2023
Document Title: Structural Drawing For Chemical Injection and Storage Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2509 |  |  | Transmital Date: 11/25/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0058_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-380072 | 1402/09/19 | مدرک فوق با ویرایش نهایی معماری انطباق داده شده است
|  |  | 1402-2294-389649 | 1402/09/25
2 |  |  | 1402-2294-380072 | 1402/09/19 | نسخه فیزیکی ارسال می گردد
|  |  | 1402-2294-389649 | 1402/09/25
3 |  |  | - | - | در این واحد از مواد اشتعال زا و هیدروکربنی نگهداری نمی شود که نیاز به محافظت و استفاده از عایق ضد حریق وجود داشته باشد
|  |  | 1402-2294-389649 | 1402/09/25
4 |  |  | 1402-2294-380072 | 1402/09/19 | مدرک AFC ارسال می گردد
|  |  | 1402-2294-389649 | 1402/09/25
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: