## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MT-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2504 |  |  | Transmital Date:11/22/2023
Document Title: MTO For Manual Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-2504 |  |  | Transmital Date:11/22/2023
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0004_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 01/2294/284190 و 02/2294/262050 اعلام شده است،مدارک MTO میبایست پس از تدوین و نهایی شدن کلیه ی مدارک مهندسی تفصیلی مربوطه تولید گردد.لذا از آن جا که تاکنون مدارک پیش گفته نهایی نشده اند،صحه گذاری و تایید این مدرک به لحاظ جنس متریال و مشخصات فنی اقلام در شرایط کنونی از سوی این امور میسر نیست.در ضمن با توجه به اینکه ویرایش ارسال شده نسبت به ویرایش پیشین تغییرات کلی داشته است لذا میبایست در مدرک نشان ویرایش درج گردد که این موضوع در مدرک ارسالی رعایت نشده است. مزید تاکید اعلام میگردد از آن جا که مسئولیت طراحی تفصیلی پروژه جزو تعهدات پیمانکار پروژه است و همچنین با استناد به وضعیت مدارک ارسالی(IFI)،مسئولیت کامل عدم تطابق متریال مندرج در این مدرک صدرالذکر (مشخصات فنی و یا تعداد) در مرحله ی سفارش گذاری و خرید برعهده ی آن پیمانکار است لذا مجدد تاکید میگردد تا زمان نهایی شدن مدارک پیشنیاز، از ارسال ویرایش جدید مدرک مدرک پرهیز گردد. |  | 1402/2294/398319 | 1402/10/02 | مدارک پیش نیاز مانند PMS و دیتاشیت ارسال شده و هر آنچه مربوط به ولو می باشد ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: