## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1315 |  |  | Transmital Date: 8/27/2022
Document Title: PMR For Differential Pressure/Pressure Gauge |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1315 |  |  | Transmital Date: 8/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0010_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | چرا جدول تجهیزات بجای ذکر در قسمت SUBJECT OF THE SUPPLY در قسمت GENERAL ذکر شده است ؟ |  | 1401-2294-216495 | 1401/06/19 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
2 | تعداد و توضیحات تجهیزات با توجه به دیتاشیت نهایی بروزرسانی گردد. |  | 1401-2294-216495 | 1401/06/19 | با توجه به توافقات صورت گرفته و مشابه دیگر مدارک MR، مدرک اصلاح گردید.
3 | صفحه 11 قسمت 11 عبارت OTHER FEE (IF ANY) حذف گردد. |  | 1401-2294-216495 | 1401/06/19 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
4 | عبارات IF Required , IF Any از مدرک حذف گردد. |  | 1401-2294-216495 | 1401/06/19 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
5 | آخرین ویرایش مدارک پیوست مدنظر قرار گیرد. |  | 1401-2294-216495 | 1401/06/19 | نظر کارفرمای محترم مدرک در تهیه این مدرک در نظر گرفته شد.
6
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: