## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2562 |  |  | Transmital Date: 2/6/2024
Document Title: Data Sheets For Manual valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2562 |  |  | Transmital Date: 2/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DT-0002_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فرآیند ساخت متریال با گرید ASTM B148 ریخته گری بوده ولی در متن مدرک ارسالی FORGED ذکر شده است که میبایست اصلاح گردد. |  | 1403-2294-18009 | 1403/01/21 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | در صورت اصلاح بند پیش گفته انتشار نسخه نهایی و با در نظر گرفتن مفاد ماده13 شرایط عمومی پیمان در خصوص مسئولیت کامل پیمانکار،پیشبرد گام بعدی مهندسی بلامانع است. |  | 1403-2294-18009 | 1403/01/21 | نقطه نظر کارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: