## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0009 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2522 |  |  | Transmital Date: 12/26/2023
Document Title: F&G Cause and Effect Diagram For Process Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2522 |  |  | Transmital Date: 12/26/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0009_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05975 | 2022-10-25 | ملاحظه شد. |  |  | بسته شد
D02
1 | در خصوص نحوه اطفای حریق در ناحیه 6،‌7،8 و 9 شفاف سازی گردد. |  | BK-SUR-ENG-INS-02-08936 | 2024-01-10 | طبق آخرین نسخه از مدرک FIRE WATER NETWORK LAYOUT ، هیچگونه Delouge Valve در نواحی 6،7،8،9 در نظر گرفته نشده است، به این دلیل اعلان حریق در این مناطق توسط اپراتورها به صورتی دستی انجام می گردد.
2 | نقطه نظرات کارفرما بپیوست ارسال می گردد. |  | BK-SUR-ENG-INS-02-08936 | 2024-01-10 | ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: