## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-IN-DW-0001 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1061 |  |  | Transmital Date: 11-Jun-2022
Document Title: Typical Instrument Installation Drawing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1061 |  |  | Transmital Date: 11-Jun-2022
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-IN-DW-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک مطابق استانداردهای نصب IPS ( از جمله IPS-D-IN-106 ) مورد بازنگری قرار گیرد. |  | 1401-2294-195659 | 1401/06/05 | با توجه به نظر کارفرمای محترم مدرک مطابق استاندارد تهیه گردید.
2 | با توجه به عنوان مدرک که نمونه نصب تجهیزات ابزاردقیق می باشد؛ لازم است برای همه تجهیزات ابزاردقیق مورد استقاده در بسته کاری نمونه نصب تجهیزات در مدرک نمایش داده شود. |  | 1401-2294-195659 | 1401/06/05 | با توجه به اینکه برای نصب تجهبزات این بسته کاری اعم از CC - PG - TG - ZI - ESDV به مدرک Instrument Hook-up Diagram رجوع می‌گردد لذا این مدرک به منظور نمایش JUNCTION BOX و CABLING ارائه گردید و تجهیزات دیگری که در این بسته کاری نیست، حذف گردید.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: