## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2326 |  |  | Transmital Date: 29-Aug-2023
Document Title: PMR For DP Flow /DP Level /Pressure/Diff. Pressure Transmitter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2326 |  |  | Transmital Date: 29-Aug-2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0011_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عبارات Sub-vendor در بخش definition of terms درج گردد. |  | 02/2294/260117 | 1402/07/04 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
2 | مسئولیت راه اندازی تجهیزات در مدارک دارای موضوعیت افزوده گردد. |  | 02/2294/260117 | 1402/07/04 | با توجه به اینکه مسئولیت راه اندازی ادوات FIELD موضوعیت ندارد، این مورد در MR های سیستم و پکیج ها لحاظ خواهد شد.
3 | در جدول تجهیزات مورد نیاز عبارت های LT , FT به LIT , FIT اصلاح گردد. |  | 02/2294/260117 | 1402/07/04 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
4 | در مدرک ذکر گردد؛ ویرابش نهایی مدارک پیوستATTACHMENT 1 جهت خرید مدنظر قرار گیرد. |  | 02/2294/260117 | 1402/07/04 | با توجه به نظر کارفرمای محترم مدرک اصلاح گردید.
5 | از آنجا که تعداد برخی ادوات از جمله LIT 2117 /2118 /2142 در جدول نیامده است نیاز است تعداد ادوات با آخرین ویرایش مدارک P&ID و INDEX مطابقت داده شده و مجددا ارسال گردد. |  | 02/2294/260117 | 1402/07/04 | مطابق توافقات و دیگر مدارک MR تمامی تگ ها حذف گردید.
6 | از آنجا که دیتاشیت برخی از ادوات هنوز تایید نهایی نشده اند نیاز است این مدرک پس از تایید نهایی دیتاشیت های مربوطه مجددا ارسال گردد. |  | 02/2294/260117 | 1402/07/04 | با توجه به نظر کارفرمای محترم مدرک مطابق آخرین نسخه از مدارک پیش‌نیاز تهیه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: