## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2621 |  |  | Transmital Date:3/5/2024
Document Title:Architectural Detail Drawing For GCS Warehouse |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-AR-T-2621 |  |  | Transmital Date:3/5/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0012_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عطف به بند 8 ریپلای شیت توضیحات مربوط به ارجاع مختصات به مدرک سازه در نوت نقشه درج گردد. |  | 1403-2294-27506 | 1403/01/28 | اعمال گردید
2 | در شیت 5/10 نبشی آبچکان در زیر سرکش در دیتایل وال سکشن درج گردد. |  | 1403-2294-27506 | 1403/01/28 | اعمال گردید
3 | ضخامت بتن مگر زیر پیاده رو در دیتایل وال سکشن مطابق با جزییات دیتایل شماره 7 مدرک 0035-DW-CV-000 به 10 سانتیمتر اصلاح گردد. در ضمن مدرک مذکور در فهرست مراجع درج گردد. |  | 1403-2294-27506 | 1403/01/28 | اعمال گردید
4 | در شیت 5/10 دیتایل وال سکشن، شیب بندی پیاده رو به سمت خارج از ساختمان،مطابق دیتایل شماره 20 مدرک 0001-000AR-DW درج گردد. |  | 1403-2294-27506 | 1403/01/28 | اعمال گردید
5 | ترنچ ورودی برق ساختمان از محدوده درب ورودی فضای 101 به داخل ساختمان به همراه داکت بانک مربوطه لحاظ گردد. |  | 1403-2294-27506 | 1403/01/28 | اعمال گردید
6 | به آگاهی می رساند، درصورت برطرف نمودن نقطه نظر یادشده در بالا، مطابق ماده 13 شرایط عمومی پیمان تصویب اسناد و مدارک فنی، مهندسی و طراحی از سوی کارفرما،از هیچ یک از مسئولیت ها و تعهدات قراردادی پیمانکار نمی کاهد، صدور ویرایش AFC این مدرک بلامانع است، بدیهی است تحقق این مهم رصد خواهد شد. |  | 1403-2294-27506 | 1403/01/28 | ارسال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: