## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2502 |  |  | Transmital Date:11/21/2023
Document Title: Geotechnical Investigation Report for Pipelines |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-2502 |  |  | Transmital Date:11/21/2023
[5 empty] | CRS No:NISOC-CRS-BK-PPL-PEDCO-320-GT-RT-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-477176 | 1402/11/18 | نتایج شیمی آب انجام گردیده لیکن هنگام جمع بندی گزارش، در پیوست افزوده نشده بود. در ویرایش حاضر، نتایج مذکور، اضافه شد. مطابق نتایج حاصل، به نظر می رسد آب رودخانه مذکور، مناسب جهت استفاده در فرآوری بتن نباشد. هرچند به دلیل فاصله زمانی طولانی بین انجام آزمایش و اجرا (نمونه گیری سال 1400) بهتر است کیفیت نمونه آب در هنگام آغاز عملیات اجرایی مورد بازرسی مجدد قرار گیرد. طی هماهنگی صورت گرفته با کارفرمای محترم(مناطق نفتخیز)، مدرک با وضعیت AFC ارسال می گردد.
2
3
4
5
6
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: