## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-PI-MT-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2615 |  |  | Transmital Date: 3/2/2024
Document Title: MTO For Insulation |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2615 |  |  | Transmital Date:3/2/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0008_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدارک MTO میبایست پس از تدوین و نهایی شدن کلیه ی مدارک مهندسی تفصیلی مربوطه تولید گردد.همچنین ازانجا که مسئولیت طراحی تفصیلی پروژه جزو تعهدات پیمانکار پروژه است و همچنین با استناد به وضعیت مدارک ارسالی(IFI) ، مسئولیت کامل عدم تطابق متریال مندرج در این مدرک صدرالذکر(مشخصات فنی و یا تعداد)در مرحله ی سفارش گذاری و خرید برعهده ی آن پیمانکار است لذا، پیگیری فرایند خرید با پذیرش تبعات پیش گفته از سوی پیمانکار بلامانع است. |  | 1403-2294-18458 | 1403/01/21 | نقطه نظر کارفرمای محترم مدنظر قرار میگیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: