## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0016 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2648 |  |  | Transmital Date: 3/18/2024
Document Title: Calculation Note For Special Pipe Supports |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2648 |  |  | Transmital Date: 3/18/2024
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ST-CN-0016_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1403-2291-43045 | 1403/02/08 | با هماهنگی بخش مکانیک به استحضار می رساند بارها و موقعیت هر ساپورت مطابق با مدرک stress analysis calculation report , single line diagram واحد مکانیک می باشد و تگ مورد نیاز هر ساپورت جهت اجرا ی پایپینگ در مدارک بخش پایپینگ نمایش داده خواهد شد
2 |  |  | 1403-2291-43045 | 1403/02/08 | لیستوفر به نقشه ها اضافه گردید
3 |  |  | 1403-2291-43045 | 1403/02/08 | پوشش امولوسیونی مطابق با نظر کارفرما در نظر گرفته شد
4 |  |  | 1403-2291-43045 | 1403/02/08 | مدرک ژئوتکنیک به قسمت ریفرنس اضافه گردید
5 |  |  | 1403-2291-43045 | 1403/02/08 | مدرک Single Line Diagram بخش پایپینگ ارسال می گردد
6 |  |  | 1403-2291-43045 | 1403/02/08 | ----
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: