## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-CN-0026 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2652 |  |  | Transmital Date:3/27/2024
Document Title: Calculation Note for Chemical Injection and Storage Shelter |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2652 |  |  | Transmital Date:3/27/2024
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-ST-CN-0026_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1403-2291-46605 | 1403/02/09 | باتوجه به کامنت های شرکت پتروایران و تغییر مقدار بار باد بر روی سازه اصلی و کنترل تغییر مکان جانبی سازه تغییرات در ابعاد ستون و تیر اجتناب ناپذیر میباشد.
2 |  |  | 1403-2291-46605 | 1403/02/09 | با توجه به هماهنگی بخش ایمنی به استحضار می رساند سایه بان مذکور از Fire potential equipment مطابق مدرک (Fire proofing zone layout(BK-GCS-PEDCO-120-SA-PY-0003)) فاصله دارد و در محدوده فایرپروفینگ قرار ندارد لذا از منظر ایمنی هیچگونه نیازی به فایرپروفینگ نیست.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: