## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-ST-DW-0021 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2469 |  |  | Transmital Date:11/6/2023
Document Title: Structural Drawing For Oily Water Sump Pit (SU-2201 B) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ST-TR-2469 |  |  | Transmital Date:11/6/2023
[5 empty] | CRS No:NISOC-CRS- BK-GCS-PEDCO-120-ST-DW-0021_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1402-2294-349987 | 1402/08/30 | مطابق با نظر کارفرمای محترم اقدام گردید
2 |  |  | 1402-2294-349987 | 1402/08/30 | لیستوفر به نقشه ها اضافه گردید
3 |  |  | 1402-2294-349987 | 1402/08/30 | لدر برای دسترسی به داخل پیت در نظر گرفته شد
4 |  |  | 1402-2294-349987 | 1402/08/30 | گریتینگ برای سقف پیت در نظر گرفته شد و جزئیات آن به نقشه ها اضافه گردید
5 |  |  | 1402-2294-349987 | 1402/08/30 | اسکرین مشبک در ورودی پیت اضافه گردید
6 |  |  | 1402-2294-349987 | 1402/08/30 | عایق داخلی برای پیت در نظر گرفته شد
7 |  |  | 1402-2294-349987 | 1402/08/30 | پیت ها بدون سایبان می باشند
8 |  |  | 1402-2294-349987 | 1402/08/30 | به مدرک استاندار گریتینگ اشاره شده است
9 |  |  | 1402-2294-349987 | 1402/08/30 | مطابق با نظر کارفرمای محترم اقدام گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: