## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0014 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2338 |  |  | Transmital Date: 9/3/2023
Document Title: Process Data Sheets For Slug Catcher |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2338 |  |  | Transmital Date: 9/3/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0014_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر تکراری: نظرات مدرک Vessel Calculation در خصوص این مدرک نیز اعمال گردد. علیرغم پذیرش این نظر در CRS، در مدرک Vessel Sizing ، نازل ورودی با فرض در نظر گرفتن Vane Pack سایز شده اما در دیتاشیت به Vane Pack اشاره ای نشده است. |  | BK-SUR-ENG-PCS-02-08422 | 2023-09-10 | Internal reinforcement plate به Inlet Flow diverter اصلاح می گردد.
2 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-02-08422 | 2023-09-10 | اعمال می گردد.
3
4
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Faramarzpour | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: