## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-CN-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2630 |  |  | Transmital Date: 3/10/2024
Document Title: HVAC Calculation Note For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-HV-TR-2630 |  |  | Transmital Date: 3/10/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-HV-CN-0002_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه کارایی و عملکرد پکیج موجود مورد تایید این امور نمی باشد، می بایست میزان بار سرمایشی پکیج مذکور از محاسبات حذف گردد و همچنین جهت تامین فشار مثبت راهکاری از جانب مشاور پروژه ارائه گردد. |  | 1403-2294-22084 | 1403/01/26 | مطابق با مذاکرات تکمیلی و توافقات صورت گرفته با کارشناس محترم مربوطه کارفرمای اصلی پروژه، سیستم تهویه مطبوع بخش توسعه ای ساختمان برق مطابق با صورتجلسه مورخ 30/11/1402 درنظر گرفته شده و مدرک با وضعیت AFD ارسال میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: