## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-HV-PY-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2585 |  |  | Transmital Date: 2/18/2024
Document Title: HVAC System Layout For CCTV Conrol Room – BINAK PU |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0012-HV-TR-2585 |  |  | Transmital Date:2/18/2024
[5 empty] | CRS No: PEDCO-CRS- BK-GCS-PEDCO-120-HV-PY-0011_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ارتفاع نصب كندانسور در نقشه قيد گردد. |  | BK-SUR-ENG-HVC-02-09092 | 2024-03-10 | ارتفاع نصب كندانسور در نقشه قيد گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: