## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-PPL-PEDCO-320-PL-DT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2564 |  |  | Transmital Date: 2/6/2024
Document Title: Data Sheets For Insulation Joints |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PL-TR-2564 |  |  | Transmital Date: 2/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-PPL-PEDCO-320-PL-DT-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند5.10 استانداردIPS-M-TP750-8میبایست در مدرک ذکر گردد که رواداری قطر داخلی IJ نباید از 2درصد قطر داخلی لوله بیشتر شود.همچنین بند 7.10استاندارد مذکور نیز در نظر گرفته شود. |  | 1402-2294-545671 | 1402/12/28 | نقطه نظر کارفرمای محترم اعمال گردید.
2 | توجه به این نکته لازم است که نقطه نظرات این امور پیشتر طی نامه شماره 01/2294/118080 مورخ1401/04/05 ارسال شده است دلیل تاخیر حدود یک سال و نیم در ارسال ویرایش جدید مشخص گردد. |  | 1402-2294-545671 | 1402/12/28 | ویرایش D01 این مدرک پس از رفع کامنت های کارفرمای محترم برروی مدرکP&ID - Gas Pipeline (to Siahmakan G.I. Station)تهیه و ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: