## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0018 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2683 |  |  | Transmital Date: 5/7/2024
Document Title: P&ID - Corrosion Inhibitor Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2683 |  |  | Transmital Date: 5/7/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0018_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | درخصوص مدرک ارسالی به پیمانکار تذکر داده می شود که می بایست یکسان سازی مدارک از سوی آن پیمانکار انجام گردد به عنوان مثال در آخرین ویرایش مدرک Duty Specification For Chemical Injection Package - Rev.D04(نامه شماره 418034)که توسط این امور نهایی گردیده است میزان Rated capacityبرای پمپ های High Pressure برابر 1.11 لیتر برساعت و برای پمپ های Low Pressure برابر 1.56 لیتر بر ساعت محاسبه و نهایی گردیده است ذر صورتی که در مدرک P&IDارسالی این مهم اصلاح نشده است واین عدم تطابق در ویرایش هشتم آن پذیرفتنی نیست. |  | 1403-2294-86973 | 1403/03/06 | در رویژن بعد اصلاح میگردد.
2 | باتوجه به محاسبات میزان تزریق مواد شیمیایی در فاز مهندسی تفصیلی NOTE 1می بایست اصلاح گردد. |  | 1403-2294-86973 | 1403/03/06 | در رویژن بعدNOTE 1 حذف می گردد.
3 | ضرورست مدرک UFD نیز به همراه این مدرک بروزرسانی و جهت نهایی سازی ارسال گردد. |  | 1403-2294-86973 | 1403/03/06 | مدرک UFD متعاقبا ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date:

## Sheet3
177500