## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MR-0004 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2357 |  |  | Transmital Date: 9/11/2023
Document Title: PMR For Manual Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2357 |  |  | Transmital Date: 9/11/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MR-0004_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 01/2294/236199 بیان گردید، ساختار کلی مدرک مورد تایید بوده ولیکن ارسال نسخه بعدی این مدرک منوط به نهایی سازی مدارک مرتبطه مهندسی و درج نسخ تایید شده(AFC) است.معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیش نیاز (که در پیوست 1 مدرک اشاره است) در دستور کار تیم مهندسی آن پیمانکار قرارگیرد. لذا مجددا تاکید میگردد تا زمان نهایی شدن مدارک پیش نیاز، از ارسال ویرایش جدید مدرک به شدت پرهیز گردد. |  | 1402-2294-263626 | 1402/07/05 | با توجه به نهایی سازی مدارک پیش نیاز مانند PMS، دیتاشیت و ... و لزوم اخذ پیشنهادات فنی کاملتر از سازندگان، مدرک به روزرسانی و ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: