## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0013 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2404 |  |  | Transmital Date: 10/4/2023
Document Title: SPECIFICATION FOR FLARE PACKAGE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2404 |  |  | Transmital Date: 10/4/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-SP-0013_D04 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پیوست های مدرک (APPENDIX) بند A1.6.1 لازم است نوع عملکرد SMOKELESS به تایید کارفرما (CLIENT) نیز برسد. شایان ذکر است با توجه به وجود گاز H2S نوع سیستم فلر بدون دود باید به صورت Air assist با قابلیت کنترل اتوماتیک در نظر گرفته شود |  | 1402-2294-337853 | 1402/08/22 | اعمال شد.
2 | همانگونه که بیشتر بارها متذکر گردیده است با توجه به تایید نهایی این مدرک، انجام تغییرات در این مقطع توجیه پذیر نیست و ضروری است ابتدا مدرک بین مجموعه پیمانکار اصلی و پیمانکار EPC نهایی شده و سپس برای کارفرما ارسال گردد از اینرو مجددا در خصوص رعایت رویه مذکور تذکر داده می شود. |  | 1402-2294-337853 | 1402/08/22 | به دلیل نیاز پروژه و تکمیل فنی مدرک، به روز رسانی و ارسال گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: