## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2639 |  |  | Transmital Date: 3/16/2024
Document Title: Stress Analysis Calculations Report |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2639 |  |  | Transmital Date: 3/16/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-RT-0002_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | علیرغم تاکید پیشین این امور مدارک اشاره شده در برگ R.Sدر پوشه NATIVE بارگذاری نشده است و لذا فایل خام محاسبات انالیز تنش به انضمام نسخه نرم افزار مربوطه ارسال نشده است |  | 1403-2294-64838 | 1403/02/22 | فایل native و نسخه نرم افزار در ویرایش قبلی بارگذاری شده بود. و حسب دستور آن کارفرمای محترم در این ویرایش نیز بارگذاری می گردد
2 | تغییرات مدرک در مدرک علاوه بر اینکه می بایت در صفحه REVISION Record مشخص گردد می بایست در متن مدرک نیز نشان داده شود |  | 1403-2294-64838 | 1403/02/22 | احتراما در هر ویرایش این مدرک محاسبات و فایل خام براساس اخرین وضعیت مدل سه بعدی و p&id به طور کامل بازبینی می گردد و report مجدد گرفته می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: