## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0012 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2578 |  |  | Transmital Date: 2/17/2024
Document Title: PMR For Flare Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2578 |  |  | Transmital Date: 2/17/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0012_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده و لیکن ارسال نسخه بعدی این مدرک منوط به نهایی سازی مدارک مرتبط مهندسی ودرج نسخه تایید شده AFC است. معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیش نیاز ( که در پیوست 1 مدرک اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. مزید تاکید اعلام میگردد از آنجا که مسولیت کامل تطابق مشخصات فنی متریال مندرج در این مدرک در مرحله سفارش گذاری و خرید بر عهده پیمانکار میباشد. |  | 1403-2294-14574 | 1403/01/20 | با توجه به تایید بیشتر مدارک پیوست 1 و عدم وجود نقطه نظر کلیدی بر مدارک ضمیمه MR ، لذا از کارفرمای محترم خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: