## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-SP-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1839 |  |  | Transmital Date: 2/1/2023
Document Title: Specification For Air Dryer Package |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1839 |  |  | Transmital Date: 2/1/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-SP-0007_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | This item is already discussed in CRS 01 version. (refer to item 1 of attahcment)
2 | "The regeneration purge rate shall be automatically adjustable". Automatic adjustable purge rate is not feasible please clarify. |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | This item is already discussed in CRS 01 version. (refer to item 2 of attahcment)
3 | "In the event of a power failure, the dryer shall continue to dry the incoming air to the specified dew point for a minimum of one hour." This time is not feasible for PSA dryers, please clarify. |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | The size of the dryer shall be designed such that in the adsorption phase, after the power cut, the dryer be able to continue to dry the intake air to the specified dew point for at least one hour. It is better to finalize this matter at TCL stage.
Instrument Comments:
1 | نقطه نظرات ذينفع اصلي بر روي اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | مطابق نظر کارفرمای محترم اصلاح شد.
2 | در خصوص ارتباط بين سيستم كنترل دراير و هواي ابزاردقيق با سيستم كنترل مركزي و ESD شفاف سازي صورت پذيرد |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | در بند 6.5 آورده شده است.
3 | لازم به ذكر است كه لزوم ارسال سيگنال ESD از سيستم ESD كل ايستگاه بررسي گردد |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | توضیحات در بند 6.5 آورده شده است. در صورت وجود سیگنال در P&ID در سیستم پکیج نیز منظورخواهد شد.
Process Comments
1 | مدرک Duty Specification for Instrument/Plant Air & Nitrogen Packages (ترنسمیتال 1809) می بایست به فهرست مدارک مرجع بخش 3.3 اضافه شود. |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
Electrical Comments
1 | Re. page 19, due to IP 65 for all equipment is not required therefore ingress protection degree for electrical equipment shall be as per “Specification for Electrical Requirements of Packaged Units; Doc. No. BK-GNRAL-PEDCO-000-EL-SP-0011”. |  | BK-SUR-ENG-MEC-01-07003 | 2023-02-25 | Noted, the discription of specification added to the phrase of standard .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: