## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ST-DW-0063 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2668 |  |  | Transmital Date: 4/21/2024
Document Title: Foundation Drawing For Extension of Existing Elect. Building |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ST-TR-2668 |  |  | Transmital Date: 4/21/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ST-DW-0063_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1403-2291-54008 | 1403/02/16 | موارد اعمال شد
2 |  |  | 1403-2291-54008 | 1403/02/16 | نامگذاری بر اساس کاربری درج گردید
3 |  |  | 1403-2291-54008 | 1403/02/16 | با توجه به عدم نهایی شدن ابعاد تجهیزات توسط وندور و کنترل نشست فونداسیون ، نیازی به فونداسیون های اشاره شده نمی باشد
4 |  |  | 1403-2291-54008 | 1403/02/16 | لیستوفر به آلبوم نقشه ها اضافه گرید
5 |  |  | 1403-2291-54008 | 1403/02/16 | با توجه به ضخامت 60 سانتیمتری نیازی به میلگرد گونه نمی باشد
6 |  |  | 1403-2291-54008 | 1403/02/16 | مختصات به تفکیک درج گردید
7 |  |  | 1403-2291-54008 | 1403/02/16 | در نقشه راهنما با توجه به کاربری ، اصلاحات صورت گرفت
8 |  |  | 1403-2291-54008 | 1403/02/16 | فایل نرم افزار به پیوست تقدیم می گردد
9 |  |  | 1403-2291-54008 | 1403/02/16 | ساختمانها به صورت ضدانفجار طراحی گردیده است
10 |  |  | 1403-2291-54008 | 1403/02/16 | لیستوفر به آلبوم نقشه ها اضافه گرید
11 |  |  | 1403-2291-54008 | 1403/02/16 | نامگذاری بر اساس کاربری درج گردید
12 |  |  | 1403-2291-54008 | 1403/02/16 | جزئیات اضافه گردید
13 |  |  | 1403-2291-54008 | 1403/02/16 | بارگذاری جرثقل در صفحه 102 موجود می باشد
14 |  |  | 1403-2291-54008 | 1403/02/16 | فایل نرم افزار به پیوست تقدیم می گردد
15 |  |  | 1403-2291-54008 | 1403/02/16 | در قسمت ریفرنس نقشه ، به مدرک فوق اشاره گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: