## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-CV-CN-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1435 |  |  | Transmital Date: 9/24/2022
Document Title: Calculation Note For Inside Surface Water Drainage Channels for GCS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-TR-1435 |  |  | Transmital Date: 9/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-CV-CN-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کانال های جمع آوری آب سطحی مربوط به جاده های فرعی - ورودی به محوطه جدید - می بایست در نقشه صفحه 6 نمایش داده شود. بنابراین پس از انجام فوق برای این مدرک نقطه نظر خاصی مطرح نخواهد بود و انجام گام های بعدی مهندسی بلامانع اعلام خواهد گردید. |  | 1401-2294-260525 | 1401/07/20 | جاده های فرعی ورودی به محوطه جدید، فاقد کانال جمع آوری آب سطحی هستند و رواناب جاده توسط کانیوو های کوچک به کانالها منتقل میشود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: