## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0024 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2437 |  |  | Transmital Date: 10/16/2023
Document Title: Mechanical Data Sheets For Flare K.O. Drum Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2437 |  |  | Transmital Date: 10/16/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0024_D06 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقطه نظر خاصي مطرح نمي باشد صرفا ميبايست نقطه نظرات احتمالي كارفرما اعمال گردد. |  | BK-SUR-ENG-MEC-02-08645 | 2023-10-23 | با توجه به عدم پذیرش تغییر کار صورت گرفته از جانب کارفرما در خصوص پمپ flare K.O drum، مطابق مدارک Basic پروژه پمپ مذکور از عمودی به افقی برگردانده شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: