## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2446 |  |  | Transmital Date: 10/22/2023
Document Title: Data Sheets For Level Gauges |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2446 |  |  | Transmital Date: 10/22/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0003_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | تگ شماره 2111C در نقشه P&ID موجود نمی‌باشد. در این مورد شفاف سازی گردد. |  | 1402/2294/328859 | 1402/08/16 | در آخرین نسخه از نقشه P&ID اضافه شده است.
2 | در مورد تگ 2281 با توجه به اینکه این LG از اندازه کمترین و بیشترین مقدار تانکی که روی آن نصب میشود 15 cm کوتاه تر است، لازم است در قالب یک نوت گفته شود که این ادوات از کف به میزان 5 cm بالاتر نصب میشود و در HOOK UP تجهیز نیز این مورد مدنظر قرار گیرد. |  | 1402/2294/328859 | 1402/08/16 | با توجه به صلاحدید کارفرمای محترم نوت مربوطه اضافه گردید و در مدل PDMS در نظر گرفته خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: