## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0015 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2430 |  |  | Transmital Date: 10/15/2023
Document Title: PMR For Level Gauge |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2430 |  |  | Transmital Date: 10/15/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0015_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم تایید نهایی مدرک دیتاشیت مربوطه لازم است این مدرک مجددا برای بررسی ارسال گردد. |  | 1402-2294-328865 | 1402/08/16 | بنا به نظر کارفرمای محترم، مدرک بر اساس آخرین نسخه از مدارک پیش نیاز تهیه گردید.
2 | تگ 2111C که در دیتاشیت می باشد در این مدرک ذکر نشده است. |  | 1402-2294-328865 | 1402/08/16 | مدرک مطابق فرمت یکسان PMR های پروژه، تهیه گردید لذا تگ تجهیزات حذف گردید.
3 | تعداد اقلام ذکر شده در بند 5.1.1 مدرک با تعداد اقلام جدول و دیتاشیت همخوانی ندارد. |  | 1402-2294-328865 | 1402/08/16
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: