## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GCS-PEDCO-120-PI-MR-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2220 |  |  |  | Transmital Date: 6/22/2023
Document Title: PMR For Flanges |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2220 |  |  |  | Transmital Date: 6/22/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MR-0003_D01 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 01/2294/364867 و 01/2294/367199 بیان گردیده است، ساختار کلی مدارک مورد تایید بوده ولیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخ تایید شده(AFC) خواهد بود.لذا صدور نسخه جدید مدرک در حالی که مدارک پیش نیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود. |  | 1402-2294-201801 | 1402/05/23 | احتراما مدارک مرتبط نظیر PMS و MTO نهایی شده است و با توجه به نیاز پروژه جهت استعلام قیمت به روز شده اتصالات پایپینگ این مدرک به روزرسانی شده است.
2 | با توجه به تغییر تیم مهندسی پیمانکار، ضروری است سوابق نفرات جدید و چارت مهندسی پروژه مجددا ارسال و بررسی گردد. |  | 1402-2294-201801 | 1402/05/23 | احتراما تغییری در تیم پایپینگ پروژه رخ نداده است. در صورت نیاز به بررسی سوابق نفرات پروژه و هر گونه چارت از مهندسی پروژه خواهشمند است این گونه موارد با واحد کنترل پروژه هماهنگ گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: