## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-MT-0003 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2217 |  |  | Transmital Date: 6/21/2023
Document Title: MTO For Flanges |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2217 |  |  | Transmital Date: 6/21/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-MT-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همان طور که در نامه های شماره 01/2294/284199 و 01/2294/284203 بیان گردیده است، مدارک MTO می بایست پس از تدوین و نهایی شدن کلیه مدارک مهندسی تفضیلی مربوطه تولید گردد. لذا از آنجا که تاکنون مدارک پیش گفته (مانند PMS ) نهایی نشده اند. صحه گذاری و تایید این مدرک به لحاظ جنس متریال و مشخصات فنی اقلام در شرایط کنونی از سوی این امور میسر نیست. از اینرو صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود |  | 1402-2294-197108 | 1402/05/18 | احتراما مدارک مرتبط نظیر PMS و مطالعات خوردگی ایستگاه تقویت فشار نهایی شده است و با توجه به نیاز پروژه جهت استعلام قیمت به روز شده اتصالات پایپینگ این مدرک به روزرسانی شده است.
2 | با توجه به تغییر تیم مهندسی پیمانکار، ضروری است سوابق نفرات جدید و چارت مهندسی پروژه مجددا ارسال و بررسی گردد. |  | 1402-2294-197108 | 1402/05/18 | احتراما تغییری در تیم پایپینگ پروژه رخ نداده است. در صورت نیاز به بررسی سوابق نفرات پروژه و هر گونه چارت از مهندسی پروژه خواهشمند است این گونه موارد با واحد کنترل پروژه هماهنگ گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: