## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-GCS-PEDCO-120-PI-MR-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2220 |  |  |  | Transmital Date: 6/22/2023 | 22.Jun.2023
Document Title: PMR For Fittings |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2220 |  |  |  | Transmital Date: 6/22/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-MR-0002_D01 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.3 موارد زير اضافه گردد : 1. ذكر گردد كه گواهينامه متريال بر اساس BS EN 10204 / ISO 10474, Type 3.2 certificate (or certificates) باشد. 2. All Materials specified with NACE shall meet the requirements of Sour Services. Sour services’ materials shall meet the requirement of NACE MR0175/ISO 15156 standard. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید. |  |  | Closed
2 | در بند 6: 1-عبارت Data Sheets به Project Specifications تغيير يابد. 2. سطح بازرسي براي Flanges and Fittings به Level 2 تغيير يابد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید. |  |  | Closed
3 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل Packing, Marking, Transportation Procedure اضافه گردد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید. |  |  | Closed
4 | عبارت " List of Documents Will be Finalized in Vendor Document index and Schedule" به عنوان نوت اضافه گردد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | اعمال گردید. |  |  | Closed
5 | نهايي شدن مدارك پيش نياز مانند PMS و Piping Wall Thickness Calculation و MTO For Fittings مربوط به GCS قبل از ارسال اين مدرك ضروري مي باشد. لذا از آنجا كه مدارك پيش نياز اين مدرك هنوز نهايي نشده است تائيد نهايي اين مدرك پس از نهايي شدن مدارك مذكور مقدور مي باشد. |  | BK-SUR-ENG-PIP-01-06285 | 29/11/2022 | مدارک مربوطه نهایی و برای کارفرمای محترم ارسال شده است.
6 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-PIP-02-08007 | 2023-07-01 | نقطه نظرکارفرمای محترم اعمال گردید.
7 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-PIP-02-08007 | 2023-07-01 | نقطه نظرکارفرمای محترم اعمال گردید.
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT or EPC/EPD CONTRACTOR (GC) before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
8 | آيتم Purchaser در بند مربوط به General Definition تعريف گردد. |  | BK-SUR-ENG-PIP-02-08007 | 2023-07-01 | طبق فرمت مدارک پروژه این آیتم موجود نمی باشد.
9 | جهت يكسان سازي در كليه متون، كلمهVendor جايگزين Supplier گردد. |  | BK-SUR-ENG-PIP-02-08007 | 2023-07-01 | نقطه نظرکارفرمای محترم اعمال گردید.
10 | در جدول Attachment 1 ، مدرك "دستورالعمل تامین قطعات یدکی راه اندازی وراهبری دو سالانه " به شماره E&C-QC-SP-01 وارد گردد. |  | BK-SUR-ENG-PIP-02-08007 | 2023-07-01 | نقطه نظرکارفرمای محترم اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: