## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2254 |  |  | Transmital Date: 2/5/2024
Document Title: PMR For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2254 |  |  | Transmital Date: 2/5/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره 02/2294/203855 و 01/2294/327165 و 01/2294/222891 بیان گردیده است، ساختار کلی مدارک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی کلیه مدارم مرتبط مهندسی و درج نسخه تایید شده (AFC) خواهد بود. لذا صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود.بدیهی است ادامه روند خرید کالا با مسئولیت کامل پیمانکار امکانپذیر خواهد بود |  | 1402-2294-487440 | 1402/11/26 | مدرک MR پکیج خوردگی به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد.با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
2 | مطابق با بند 2 برگ R.S میبایست سوابق نفرات جدید و چارت مهندسی پروژه ارسال گردد که این مهم تا کنون محقق نشده است. |  | 1402-2294-487440 | 1402/11/26 | سوابق نفرات و چارت مهندسی متعاقبا ارسال خواهد شد.
3 | همانگونه که بارها تاکید شده است کلیه مدارک میبایست ابتدا در مجموعه پیمانکار( پیمانکار اصلی و پیمانکار EPC) نهایی شده و سپس برای کارفرما ارسال گردد. لذا ارائه مدرک پیش از طی این مرحله اقدام زود هنگام به شمار رفته و سبب تطویل بررسی و نهایی سازی مدارک خواهد بود لذا تاکید میگردد از ادامه روند ناصحیح به شدت پرهیز گردد |  | 1402-2294-487440 | 1402/11/26 | .با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: