## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0017 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2622 |  |  | Transmital Date: 3/6/2024
Document Title: Mechanical Data Sheets For Fire Water Storage Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2622 |  |  | Transmital Date: 3/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0017_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نام گذاری نازل ها بر روی شکل شماتیک با جدول نازل لیست مغایرت دارد که می بایست اصلاح گردد. به عنوان نمونه نازل A2 به عنوان نازل سایز 10 اینچ Pressure relife valve درج شده است درحالی که در شماتیک دارای ابعاد و محل صحیح نیست |  | 1403-2294-18392 | 1403/01/21 | - در خصوص نازل ها این مورد در Sketch و جدول نازل ها اصلاح شده است.
2 | با توجه به اینکه محاسبات مخزن ارسال نشده است. مبنای محاسبه و درج ضخامت ها بیان گردد. |  | 1403-2294-18392 | 1403/01/21 | - در خصوص ضخامت ها به این مورد پس از عقد قرار داد و بر اساس محاسبات دریافتی از سازنده نهایی می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: