## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0023 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2210 |  |  | Transmital Date: 6/18/2023
Document Title: Process Data Sheets For Closed Drain Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2210 |  |  | Transmital Date: 6/18/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0023_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک DT-0023 با وضعیت HOLD توسط کارفرما پاسخ داده شده است و مورد HOLD که مربوط به ارائه فرم تغییرات پمپها بوده هنوز توسط پیمانکار ارائه نشده است، لذا این ترنسمیتال به پیمانکار عودت می گردد. |  | EMAIL | 2023-06-20 | نوع پمپ و محاسبات مربوطه تغییر داده شده و مدرک به روزرسانی گردید.
2
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: