## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0011 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2624 |  |  | Transmital Date: 3/6/2024
Document Title: P&ID - 2nd Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2624 |  |  | Transmital Date: 3/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0011_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه جلسه مربوط به HAZOP کمپرسور های گازی پس از تایید این مدرک برگزار شده است، لذا پیمانکار می بایست توصیه های مربوط به صورتجلسه HAZOP کمپرسور را ملاک عمل قرار دهد. |  | 1403-2294-78133 | 1403/02/30 | مورد تایید است.
2 | با توجه به تغییر وضعیت عملکرد شیر و BDV-2132 در سیستم کنترل اصلی کارخانه و سیستم کنترل کمپرسور نسبت به مهندسی تفصیلی و پیش از قرارداد با سازنده ضروریست تا دلیل تغییرات و آخرین توافقات با سازنده بر اساس مذاکرات حاشیه جلسه HAZOP به اطلاع کارفرما رسانده شود. لازم به ذکر است که این اقدام نیز بدون اطلاع کارفرما انجام شده است. |  | 1403-2294-78133 | 1403/02/30 | مطابق توافقات جلسه hazop و
3 | از آنجاییکه میزان Duty اعلامی در مدرک ارسالی با میزان Duty در نظر گرفته شده توسط سازنده کولر هوایی متفاوت می باشد، لذا ضروریست در این خصوص توضیحات لازم از سوی پیمانکار ارائه گردد. |  | 1403-2294-78133 | 1403/02/30 | در این رویژن میزان Duty که توسط سازنده محاسیه گردیده است اضافه خواهد گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: