## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DT-0016 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2612 |  |  | Transmital Date: 3/2/2024
Document Title: Data Sheets For F&G Detectors & Equipment |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2612 |  |  | Transmital Date: 3/2/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DT-0016_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مورد بند 1 تا 3 R.S. مربوط به SMART HART بودن ادوات، علی رغم تایید این موضوع در پاسخ پیمانکار اصلاحی صورت نگرفته است. لازم است این موارد اصلاح گردند. |  | 1402-2294-542156 | 1402/12/27 | مدرک مطابق خواست کارفرمای محترم اصلاح و بروز رسانی گردید.
2 | در صفحه 8 مدرک لازم است منبع تغذیه بصورت 24VDC LOOP POWERED در نظر گرفته شود. برای سایر ادوات هم این مورد صدق می نماید. |  | 1402-2294-542156 | 1402/12/27 | مدرک مطابق خواست کارفرمای محترم اصلاح و بروز رسانی گردید.
3
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: