## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2536 |  |  | Transmital Date: 1/29/2024
Document Title: I&C Power Consumption Summary |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2536 |  |  | Transmital Date: 1/29/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | دلیل استفاده از ضریب ۱.۵ برای Contingency چیست؟ |  | 1402-2294-504206 | 1402/12/07 | مدرک مطابق توافقات جلسه مورخ ۱۴۰۳/۰۵/۱۴ اصلاح شد.
2 | از آنجا که سازنده کمپرسور و نمزدا مشخص شده است ، لازم است مستندات توان مصرفی این دو پکیج ارايه گردد. |  | 1402-2294-504206 | 1402/12/07 | مدرک مطابق توافقات جلسه مورخ ۱۴۰۳/۰۵/۱۴ اصلاح شد. مستندات در فایل های ضمیمه ارايه شده است.
3 | با توجه به تفاوت چشمگیر توان مصرفی اعلام شده در این مدرک با اسناد پایه پیمان ، ضرورت دارد آن پیمانکار جهت شفاف سازی و تسریع در نهایی سازی مدرک ،‌هر چه سریعتر برای برگزاری جلسه ای با حضور نمایندگان کارفرما و پیملنکار اعلام آمادگی نماید. |  | 1402-2294-504206 | 1402/12/07 | جلسه در تاریخ ۱۴۰۳/۰۵/۱۴ برگزار شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: