## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2643 |  |  | Transmital Date: 3/16/2024
Document Title: PMR For Centrifugal Pumps For General Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2643 |  |  | Transmital Date: 3/16/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0010_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه های شماره02/2294/201743، 01/2294/231560 و 01/2294/371137 بیان گردیده است، ساختار کلی مدارک مورد تایید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی کلیه مدارک مرتبط مهندسی و درج نسخ تایید شده (AFC) خواهد بود. لذا صدور نسخه جدید مدرک در حالی که مدارک پیشنیاز به طور کامل نهایی نشده است توجیه پذیر نبوده و تنها سبب مکاتبات مضاعف خواهد بود. در ضمن مزید تاکید اعلام میگردد از آنجا که مسئولیت طراحی تفضیلی پروژه جزو تعهدات پمیانکار پروژه بوده و همچنین با استناد به وضعیت مدرک ارسالی (IFI)، مسئولیت کامل عدم تطابق متریال مندرج در این مدرک (مشخصات فنی و یا تعداد) در مرحله سفارش گزاری و خرید بر عهده آن پیمانکار بوده و از اینرو پیشبرد گام بعدی امکانپذیر است. |  | 1403-2294-100338 | 1403/03/16 | مدرک PMR FOR CENTRIFUGAL PUMPS FOR GENERAL SERVICES به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد. با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: