## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0010 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2643 |  |  | Transmital Date: 3/16/2024
Document Title: PMR For Centrifugal Pumps For General Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-2643 |  |  | Transmital Date: 3/16/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0010_D03 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
4 | در اين برهه نقطه نظر خاصي مطرح نمي باشد . صرفا مي بايست نظرات احتمالي ذينفع اصلي پروژه بر روي اين مدرك اعمال گردد.شایان ذکر است با توجه به مفاد 13 شرایط عمومی پیمان, مسئولیت هر نوع نقص و کمبود در نقشه ها و مدارک فنی در محدوده پروژه و در هر مقطع از پروژه اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد بر عهده پیمانکار است. همچنين لازم به ذكر است كه مسئوليت بروزرساني ويرايش مدارك پيوست مندرج در اين مدرك ، پس از نهايي شدن آنها ، بر عهده آن پيمانكار مي باشد. |  | BK-SUR-ENG-MEC-03-09194 | 2024-04-06 | مدرک PMR For Centrifugal Pumps For General Services به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد.با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: