## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2623 |  |  | Transmital Date: 3/6/2024
Document Title: P&ID - 1st Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2623 |  |  | Transmital Date: 3/6/2024
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فشار طراحی می بایست مطابق آخرین مذاکرات صورت گرفته و مدارک سازنده برابر 24.5Barg لحاظ گردد درصورتیکه در مدرک برابر 22Barg درنظر گرفته شده است این مهم قبلاً نیز طی نامه 438763 مورخ 26/10/1402 مربوط به داده برگ اطلاعات فنی ارسالی از سوی سازنده (شرکت کولر هوایی آبان) اعلام شده است. |  | 1403-2294-35542 | 1403/02/03 | فشار 24.5 barg مربوط به Casing کمپرسور میباشد و فشار طراحی 22 barg مطابق با محاسبات settle out کمپرسور در نظر گرفته شده است.
2 | از آنجائیکه میزان Duty اعلامی در مدرک ارسالی با میزان Duty درنظر گرفته شده توسط سازنده متفاوت می باشد، لذا مقتضی است تا توضیحات لازم ارائه گردد. |  | 1403-2294-35542 | 1403/02/03 | میزان Duty مطابق با مدارک سازنده به روز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: