## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-PI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2623 |  |  | Transmital Date: 3/6/2024
Document Title: P&ID - 1st Stage Gas Compression Air Coolers |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2623 |  |  | Transmital Date: 3/6/2024
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-PI-0008_D08 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با اعمال نظرات ذیل، مدرک مورد تایید می باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی ما بین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. |  | BK-SUR-ENG-PCS-03-09179 | 2024-03-30 | مورد تایید می باشد.
2 | Duty درج شده برای این تجهیز با آخرین ویرایش داده برگ سازنده مطابقت ندارد. |  | BK-SUR-ENG-PCS-03-09179 | 2024-03-30 | مطابق با مدرک سازنده به روز رسانی گردید.
3 | نظر عمومی: NOTE-7 به این صورت اصلاح گردد که تمامی Vent ها نیز به شبکه فلر متصل گردد. این مورد در تمامی صفحات اصلاح گردد |  | BK-SUR-ENG-PCS-03-09179 | 2024-03-30 | اعمال گردید.
4 | نظرات ذینفع اصلی پروژه در مدرک اعمال گردد. |  | BK-SUR-ENG-PCS-03-09179 | 2024-03-30 | مورد تایید می باشد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: